## Estimation
# | Area | Task | Priority | TOTAL (hrs) | Notes
Cross-Cutting / Platform-Wide
1 | Cross-Cutting | Migrate LLM from OpenAI API to local model (Ollama) | Blocker | 8 | Add provider abstraction; swap all call sites: case eval, case generation, questions, rapid-fire.
2 | Cross-Cutting | Fix LLM reliability (~50% working -> consistent) | High | 8 | Error handling, JSON-schema/prompt consistency, retries, timeouts, fallbacks.
3 | Cross-Cutting | Reports & Analytics from student answers (currently pending) | High | 16 | Scoring aggregation, per-student/section reports, backend endpoints + frontend views + charts.
Admin Portal
4 | Admin | Fix 'Create Section' (blocks entire downstream flow) | Blocker | 3 | Root-cause + fix section creation; unblocks faculty & student testing.
5 | Admin | Assign faculty (teacher) to sections/students - UI + wiring | Blocker | 4 | Backend endpoints exist; build/repair UI + verify faculty_sections linkage.
6 | Admin | Fix bulk user import (template download + import) | High | 3 | Fix template endpoint and CSV import parsing/validation.
7 | Admin | Add user invite flow (currently manual-only) | High | 3 | Invite email + token acceptance + account activation.
8 | Admin | Admin views: faculty-uploaded cases, student attempts, reports | High | 8 | New read/list screens for cases per faculty + attempt status + analytics.
9 | Admin | Update admin dashboard to reflect new data/views | Medium | 3 | Rework KPI cards/widgets per new sections.
10 | Admin | Role cleanup (Faculty/Mentor/Director scope confirmation) | Medium | 4 | Hide/remove roles not required after stakeholder confirmation.
11 | Admin | Clarity + fixes: Courses, Sections, Settings, Notifications | Medium | 8 | Define behavior, tidy UI, wire missing bits.
Faculty Portal
12 | Faculty | Assign case to a particular student or group (new capability) | High | 4 | New endpoint (per-student/group) + assignment UI; extends section-only assign.
13 | Faculty | Add student manually + invite flow in faculty portal | Medium | 4 | Manual add + invite, respecting section enrollment.
14 | Faculty | Rubric Builder visibility after save (nav/wiring fix) | High | 3 | Route rubric to /rubric-builder/:caseId and surface saved rubric.
15 | Faculty | Rapid-fire timer (missing) | Medium | 8 | Timed round countdown, wired to rapid_fire timing fields.
16 | Faculty | Automatic time calculation (missing) | Medium | 5 | Auto-compute reading/writing/rapid-fire totals from inputs.
17 | Faculty | Verify case-to-class assign + students-assigned-to-faculty | Medium | 3 | Regression check once Admin section/linkage fixed.
Student Portal
18 | Student | End-to-end student flow enablement + fixes | High | 35 | 6-screen attempt flow (start->analysis->AI->solution->defense->reflection) once linkage works.
Integration & QA
19 | Integration | Full Admin -> Faculty -> Student integration testing |  | 12 | End-to-end scenario runs, defect fixing, regression.
20 | Integration | Bug-fix / stabilization pass |  | 8 | Buffer for issues found during integration.
|  | TOTAL |  | 150

## Summary by Area
Area | Base (hrs) | Buffer (hrs) | Total (hrs)
Cross-Cutting | 42 | 10.5 | 52.5
Admin | 47 | 11.5 | 58.5
Faculty | 26 | 7 | 33
Student | 8 | 2 | 10
Integration | 14 | 3.5 | 17.5
GRAND TOTAL | 137 | 34.5 | 171.5
Assumptions & Notes
1. Estimates assume development is Claude Code-assisted (coding accelerated); time still budgeted for iteration, testing, debugging & review.
2. Buffer = 25% per task (rounded to nearest 0.5 hr) for unexpected delays / rework.
3. Hours are engineering effort, not calendar time (excludes meetings, reviews, waiting on clarifications).
4. 'Blocker' items (Create Section, faculty->section linkage, local LLM) should be done first - they unblock other tasks.
5. Reports & Analytics and Local-LLM migration are the two largest efforts.
6. Some Faculty/Student items are partly gated by Admin fixes; verification hours assume those land first.