PCDC

Prestige Capability Development Centre

SCOPE OF WORK (SOW)

Remediation & Feature Completion Engagement

Version 1.0  |  Date: 30 July 2026

| Field | Detail |
| --- | --- |
| Document | Scope of Work - PCDC Remediation & Feature Completion |
| Based on | PCDC Findings Report & Time Estimation (v29 Jul 2026) |
| Prepared by | Development Team |
| Status | Draft for review / sign-off |
| Total estimated effort | 150 engineering hours (Claude Code-assisted) |

# 1. Introduction & Background

PCDC (Prestige Capability Development Centre) is an AI-powered capability development platform for business students, comprising an Admin portal, a Faculty portal and a Student portal, backed by a FastAPI service, a PostgreSQL (Neon) database and a React/Vite frontend.

A QA review identified a set of defects, missing features and platform-wide gaps that currently prevent the product from being tested and used end-to-end. This Scope of Work defines the work required to remediate those findings, complete the missing features, and deliver a fully functioning, integrated Admin -> Faculty -> Student flow. It is derived directly from the PCDC Findings Report & Time Estimation.

# 2. Objectives

Restore the end-to-end Admin -> Faculty -> Student flow by fixing the core linkage blockers.

Migrate the AI/LLM layer from the OpenAI API to a locally hosted model and make it reliable across all AI-driven steps.

Complete missing Admin and Faculty features (user onboarding, assignment, visibility, timing).

Build Reports & Analytics based on student answers.

Audit and stabilize existing APIs and validate the complete platform through integration testing.

# 3. Scope of Work

The work is organized into seven workstreams. Each workstream lists its deliverables, acceptance criteria and indicative effort. Effort figures align with the approved time estimation (150 hours total).

## 3.1 Workstream 1 - Core Linkage & Blockers

Priority: Blocker    |    Indicative effort: 10 hrs

Unblocks all downstream faculty and student testing.

Deliverables:

Root-cause and fix Admin 'Create Section' so sections can be created reliably.

Build/repair the Admin UI to assign faculty to sections and verify the faculty_sections linkage.

Verify students appear against their faculty and that faculty can assign cases to a class once sections exist.

Acceptance criteria:

An admin can create a course -> batch -> semester -> section without error.

An admin can assign a faculty member to a section, and that faculty then sees the section, its students and can assign a case to it.

Students enrolled in a section appear in the faculty roster.

## 3.2 Workstream 2 - AI / Local LLM

Priority: Blocker/High    |    Indicative effort: 16 hrs

Aligns the AI layer with the requirement to run locally and makes it dependable.

Deliverables:

Introduce a provider abstraction and migrate all AI call sites from OpenAI to a local model (Ollama): case generation, question generation, rapid-fire generation, student analysis evaluation, AI coaching dialogue, and defense/reflection scoring.

Add robust error handling, JSON-schema/prompt consistency, retries, timeouts and fallbacks so results are consistent across every AI-driven step.

Acceptance criteria:

No AI feature calls the OpenAI API; all inference runs against the local model.

Each AI-driven step returns valid, schema-conformant output consistently across repeated runs (no intermittent failures).

## 3.3 Workstream 3 - Admin Portal Features

Priority: High/Medium    |    Indicative effort: 29 hrs

Completes admin onboarding, visibility and configuration.

Deliverables:

Fix bulk user import: repair the template download and the CSV import (parsing + validation).

Add a user invite flow (invite email + token acceptance + account activation).

Build admin visibility screens: case studies uploaded by faculty, student attempt details (who attempted what), and reports & analytics.

Update the admin dashboard to reflect the new data and views.

Role cleanup: confirm required roles and hide/remove those not in scope (Faculty/Mentor/Director as applicable).

Define and tidy Courses, Sections, Settings and Notifications behavior.

Acceptance criteria:

Admin can download a valid import template and successfully bulk-import users.

Admin can invite a user who can then activate their account.

Admin can view faculty-uploaded cases and per-student attempt status; dashboard reflects these.

Only in-scope roles are presented; Courses/Sections/Settings/Notifications behave as documented.

## 3.4 Workstream 4 - Faculty Portal Features

Priority: High/Medium    |    Indicative effort: 24 hrs

Completes faculty assignment and case authoring capabilities.

Deliverables:

Add ability to assign a case to a particular student or a group of students (new endpoint + UI), extending the current section-only assignment.

Add manual add + invite student flow within the faculty portal (respecting section enrollment).

Fix Rubric Builder visibility so a saved rubric is surfaced after creation (route to /rubric-builder/:caseId).

Implement the rapid-fire round timer wired to the rapid-fire timing fields.

Implement automatic time calculation (reading/writing/rapid-fire totals) from inputs.

Acceptance criteria:

Faculty can assign a case to an individual student or a selected group, not just a whole section.

A saved rubric remains visible/editable after it is built.

The rapid-fire round runs against a countdown timer; total timings are auto-calculated.

## 3.5 Workstream 5 - Reports & Analytics

Priority: High    |    Indicative effort: 16 hrs

Delivers the currently-pending reporting on student performance.

Deliverables:

Build scoring/aggregation logic on student responses.

Build per-student and per-section reports with backend endpoints.

Build frontend analytics views and charts for faculty/admin.

Acceptance criteria:

Faculty/Admin can view meaningful reports of how students answered and performed, at student and section level.

## 3.6 Workstream 6 - Student Portal Enablement

Priority: High    |    Indicative effort: 35 hrs

Enables and validates the full student experience, unblocked by WS1.

Deliverables:

Enable and complete the 6-step attempt flow: briefing -> analysis -> AI dialogue -> solution -> defense -> reflection.

Fix defects surfaced across the student journey once linkage and AI are in place.

Acceptance criteria:

A student can receive an assigned case and complete all six steps, producing a scored evaluation and updated capability profile.

## 3.7 Workstream 7 - Existing API Audit, Integration & QA

Priority: High    |    Indicative effort: 20 hrs

Confirms overall correctness and stabilizes the platform.

Deliverables:

Perform a full audit/regression pass across all existing endpoints (auth, admin, faculty, student, simulation/attempt, capability, notification) and fix defects found.

Run full Admin -> Faculty -> Student integration test scenarios.

Dedicated bug-fix / stabilization pass for issues found during integration.

Acceptance criteria:

All existing endpoints behave as expected with no known blocking defects.

A complete end-to-end scenario (admin setup -> faculty case + assign -> student attempt -> reporting) passes.

# 4. Deliverables Summary & Effort

| Workstream | Priority | Effort (hrs) |
| --- | --- | --- |
| WS1 - Core Linkage & Blockers | Blocker | 10 |
| WS2 - AI / Local LLM | Blocker/High | 16 |
| WS3 - Admin Portal Features | High/Medium | 29 |
| WS4 - Faculty Portal Features | High/Medium | 24 |
| WS5 - Reports & Analytics | High | 16 |
| WS6 - Student Portal Enablement | High | 35 |
| WS7 - Existing API Audit, Integration & QA | High | 20 |
| TOTAL |  | 150 |

Indicative duration: At ~6 productive hours/day, 150 hours is approximately 25 working days (~5 weeks). At ~8 hours/day, approximately 19 working days (~4 weeks). These are engineering-effort figures and exclude meetings, reviews and time spent waiting on clarifications.

# 5. Phasing & Milestones

Work is sequenced so that blockers are resolved first and each phase unblocks the next.

| Phase | Focus | Workstreams | Milestone / Exit criteria |
| --- | --- | --- | --- |
| 1 | Unblock foundation | WS1 | Sections created + faculty/student linkage verified |
| 2 | AI local migration & stability | WS2 | All AI runs locally & reliably |
| 3 | Admin features | WS3 | Onboarding, visibility & dashboard complete |
| 4 | Faculty features | WS4 | Assignment, rubric, timing complete |
| 5 | Reports & Analytics | WS5 | Student-answer reporting live |
| 6 | Student enablement | WS6 | 6-step attempt flow validated |
| 7 | API audit, integration & QA | WS7 | End-to-end scenario passes; no blocking defects |

# 6. Approach & Methodology

Development is Claude Code-assisted; coding is accelerated while time is still budgeted for iteration, testing, debugging and review.

Blocker-first sequencing: the Admin section/linkage fix and the local-LLM migration are prioritized because they unblock the most downstream work.

Each workstream is closed against its acceptance criteria before the dependent phase begins.

Existing endpoints are audited and regression-tested rather than assumed correct.

Changes to the database use Alembic migrations; no direct schema edits.

# 7. Out of Scope

Unless explicitly agreed and added via change request, the following are out of scope:

New features not listed in the findings report or this SoW.

Production hosting, infrastructure provisioning, and procurement of GPU/compute for the local LLM (assumed available).

Third-party integrations beyond email notifications (e.g. WhatsApp) unless separately scoped.

Data migration beyond what is required for testing.

Mobile-native applications; work targets the existing web application.

# 8. Assumptions & Dependencies

A local LLM runtime (e.g. Ollama) and adequate compute are available in the target environment.

Stakeholders will promptly confirm open questions (required roles; behavior of Courses/Sections/Settings/Notifications).

The team has access to the codebase, database and environments needed for development and testing.

Effort estimates assume Claude Code-assisted development and a 25% buffer already reflected in task-level figures.

Some Faculty/Student items are gated by the Admin linkage fixes landing first.

# 9. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Local LLM output quality/consistency lower than OpenAI | AI steps unreliable | Provider abstraction + schema validation, retries and fallbacks; evaluate model choice early |
| Existing API defects broader than expected | Timeline slippage | Front-load the audit; triage and prioritize blockers |
| Open scope questions delayed (roles, module behavior) | Rework | Confirm in Phase 1; proceed on documented assumptions otherwise |
| Blocker fixes reveal deeper data-model issues | Effort increase | Root-cause in WS1 before dependent phases start |

# 10. Overall Acceptance Criteria

A complete Admin -> Faculty -> Student scenario can be executed end-to-end without blocking defects.

All AI-driven steps run on the local LLM and produce consistent, valid outputs.

Reports & Analytics on student answers are available to faculty/admin.

All existing endpoints pass the audit/regression pass.

Each workstream meets its stated acceptance criteria.

# 11. Roles & Responsibilities

| Role | Responsibility |
| --- | --- |
| Development Team | Implementation, testing, bug-fixing across all workstreams |
| QA | Integration testing, regression, defect verification |
| Product / Stakeholders | Clarify scope questions, review and sign off deliverables |
| Client / Owner | Provide environment, local-LLM compute, and acceptance sign-off |

# 12. Sign-off

By signing below, the parties agree to the scope, deliverables and estimates described in this document.

| Name | Role | Signature | Date |
| --- | --- | --- | --- |
|  | Client / Owner |  |  |
|  | Delivery Lead |  |  |