Work Breakdown Structure

Prestige Capability Development Centre (PCDC)

Proof of Concept — Staff Portal & Student Portal

Timeline: 27 working days (≈ 5 weeks)

22-day build  +  1-week extension for UAT & Production Release

Contents

# 1. Introduction

This document presents the scope and Work Breakdown Structure (WBS) for the Proof of Concept (PoC) of the Prestige Capability Development Centre (PCDC) — an AI-powered capability development and assessment platform.

PCDC replaces traditional answer-based testing with capability evaluation. Students solve real-world case studies using AI as a professional tool; an AI engine then interrogates and scores how they think — not just what they answered — and tracks their growth across difficulty levels. The platform comprises two applications: a role-gated Staff Portal (Admin & Mentor) and a Student Portal, sharing a common AI evaluation and level-progression engine.

Delivery is planned over 27 working days (≈ 5 weeks): a 22-working-day build followed by a 1-week extension for UAT and Production Release. The first client demo is conducted on the UAT environment, leading to a UAT sign-off and then production go-live. The sections below cover the user types, technology, team/resourcing, the features of each portal (with the end-to-end flow), and a day-estimated WBS broken down by Module → Task → Subtask across Frontend (FE), Backend (BE), Database (DB) and AI work, with weekly sign-offs.

# 2. User Types

| User Type | Portal | Description & Key Access |
| --- | --- | --- |
| Admin | Staff Portal | Institution superuser. Manages the domain master list, invites mentors and assigns domains, bulk-imports students, sees all reports and cross-domain analytics, and manages settings. |
| Mentor (Faculty) | Staff Portal | Subject expert assigned one or more domains. Authors and launches case studies, reviews student answers and AI scores, gives feedback, and unlocks students — scoped to assigned domains. |
| Student | Student Portal | Learner pre-mapped to a domain (from college data). Takes AI-evaluated case studies, progresses through levels, and tracks their capability growth. |

# 3. Technology Stack

| Layer | Technology | Purpose |
| --- | --- | --- |
| Frontend | Next.js (React) + Tailwind CSS | Admin and Student web portals. |
| Backend | Python + FastAPI | APIs, business logic, AI orchestration. |
| Database | PostgreSQL | Domains, users, case studies, attempts, scores. |
| AI / LLM | Hosted LLM API via provider abstraction (architected for Llama 3.3 in production) | Answer analysis, rapid-fire questions, suggestions and weighted scoring. |
| Authentication | JWT + email/password (temporary-password onboarding) | Secure, role-based access. |
| Email | Transactional email service | Invitations, credentials and notifications. |
| Hosting | Cloud (dev / UAT / production) | Environments for development, UAT and go-live. |

# 4. Team & Resourcing

| Role | Allocation | Responsibilities |
| --- | --- | --- |
| Full-Stack Developer (with AI) | 100% — 8 hrs/day | All Frontend, Backend, Database and AI-engine development; UAT & production defect fixes; deployment support. |
| Project Manager (PM) | 40% bandwidth | Planning & coordination, client communication, weekly sign-offs, UAT facilitation and go-live sign-off. |
| QA / Tester | Weekly sanity + full regression at UAT & Go-Live | Sanity testing each week during development; regression testing during UAT and at production go-live. |
| DevOps Engineer | 30% bandwidth | CI/CD, environment setup (dev / UAT / production), UAT & production deployment, monitoring. |

Note: the developer is the single full-time builder; PM, QA and DevOps contribute at the bandwidths above. QA runs a weekly sanity pass during the build and full regression at UAT and go-live.

# 5. Admin / Staff Portal — Features

| Feature | Description & Flow |
| --- | --- |
| Authentication & Invitations | Secure login. Admin invites a mentor by email; the mentor receives a temporary password and is forced to set a new password on first login. |
| Domain Management | Admin maintains a static master list of domains (subjects). Domains anchor every case study and every student. |
| Mentor Management & Domain Assignment | Admin invites mentors and assigns each one or more domains. Mentors can only access their assigned domains; multiple mentors may share a domain (authorship of each case study is tracked). |
| Student Provisioning | Admin bulk-imports students from college data (CSV) with their domain. Each student is initialised at Level 1 and emailed login credentials. |
| Case Study Authoring | Mentors create case studies — scenario (situation, data, constraints, objective), difficulty level (Beginner / Intermediate / Hard) and target domain(s) — saved as a draft. |
| Launch & Time Window | Mentors publish a case study to matching students, setting a fixed open→close window and/or a per-attempt countdown timer. |
| Reporting & Feedback | Mentors view each student's typed answer, the AI rapid-fire Q&A, the score breakdown and attempt history; add written feedback; and unlock students who have exhausted their attempts. |
| Dashboards & Analytics | Admin sees institution-wide counts and cross-domain rollups; mentors see their domains, their case studies and students needing attention. |

# 6. Student Portal — Features

| Feature | Description & Flow |
| --- | --- |
| Registration & Login | Student receives an email with their login and a temporary password, and sets a new password on first login. |
| Dashboard | Shows overall capability score, current domain & level, available case studies, progress across levels, and recent mentor feedback. |
| Case Study Discovery | The student sees case studies for their domain at their current unlocked level. Higher levels stay locked until the previous level is passed. |
| AI Assessment Loop | Read the scenario → type the answer (copy-paste disabled, AI engages only after submitting) → AI asks 3–4 rapid-fire questions → AI returns suggestions on what is missing → the student submits one revision → the AI gives a final score across 6 dimensions (Thinking Depth, Logic, Creativity, Practicality, Risk Awareness, Reflection). |
| Level Progression | Score ≥ 75% auto-advances to the next level; 33–<75% allows a retry (up to 4 attempts); a locked level prompts the student to contact their mentor. |
| Capability Profile | The student tracks capability scores and growth over time — competing against themselves, not peers. |
| Feedback & Notifications | The student reads mentor feedback and is notified of new case studies, results, level unlocks and locks. |

# 7. End-to-End Flow (Summary)

- Admin sets up domains and invites mentors (assigning domains); students are bulk-imported with their domain and emailed credentials.

- A mentor authors a case study at a chosen level and launches it with a time window.

- A matching student opens it, types an answer (paste blocked), and submits — only then does the AI engage.

- The AI asks 3–4 rapid-fire questions, returns suggestions, and the student submits one revision.

- The AI produces a weighted final score; ≥75% auto-advances, 33–<75% allows retry (max 4), exhaustion locks the level until a mentor unlocks.

- Capability scores update; mentors review the full thinking path and intervene where needed.

# 8. Work Breakdown Structure

Estimates are in working days, summing to 27 (22-day build + 1-week UAT & production release). Layers: FE = Frontend, BE = Backend, DB = Database, AI = AI engine, Plan = design/planning, QA = testing, DevOps = environments/deployment, PM = project management, Dev = developer fixes.

## 8.1 Phased Timeline & Weekly Sign-offs

| Week | Days | Focus | Output / Sign-off |
| --- | --- | --- | --- |
| Week 1 | Day 1–5 | Design & planning, foundation/setup, authentication & user management | Design & wireframes approved; environments ready; login + onboarding working. |
| Week 2 | Day 6–10 | Domains, mentor management, case-study authoring & launch, AI engine begins | Admin & mentor management + case-study authoring/launch demonstrated. |
| Week 3 | Day 11–15 | AI engine completed + student assessment loop | AI evaluation engine + full student attempt working end-to-end. |
| Week 4 | Day 16–20 | Progression, capability scoring, reporting, dashboards, notifications | Feature-complete build (all modules). |
| Week 5 | Day 21–25 | Internal QA & polish, then UAT deploy, first demo on UAT, fixes & regression | UAT SIGN-OFF (client acceptance on UAT). |
| Week 6 | Day 26–27 | Production release & go-live regression | PRODUCTION GO-LIVE SIGN-OFF. |

## 8.2 Module Timeline Summary

| Module / Epic | Effort | Timeline | Key Outcome |
| --- | --- | --- | --- |
| EPIC 0 — Designing & Planning | 2d | Day 1–2 | Approved FRD, wireframes, DB schema & API contract; project plan ready. |
| EPIC 1 — Foundation & Setup | 1d | Day 3 | Running skeleton of backend, frontend and DB; deploy pipeline ready. |
| EPIC 2 — Authentication & User Management | 2d | Day 4–5 | Login works; mentors invited and students bulk-provisioned with temp-password onboarding. |
| EPIC 3 — Domain Management | 1d | Day 6 | Admin maintains the static domain master list. |
| EPIC 4 — Mentor Management & Domain Assignment | 1d | Day 7 | Mentors assigned to domains; access scoped to assigned domains. |
| EPIC 5 — Case Study Authoring & Launch | 2d | Day 8–9 | Mentors author case studies (level + domains) and launch them with a time window. |
| EPIC 6 — AI Engine | 3.5d | Day 10–13 | Full AI evaluation: analysis, rapid-fire questions, suggestions and weighted scoring — reliable & swappable. |
| EPIC 7 — Student Assessment Loop | 2.5d | Day 13–15 | Student completes a case study end-to-end: briefing → paste-blocked answer → rapid-fire → suggestions → 2nd submission → score. |
| EPIC 8 — Level Progression Engine | 1d | Day 16 | Auto-advance, retry (max 4), configurable <33% rule, lock + mentor unlock. |
| EPIC 9 — Capability Scoring & Profile | 1d | Day 17 | Capability scores update from attempts; student sees profile + growth trend. |
| EPIC 10 — Reporting & Feedback | 1.5d | Day 18–19 | Mentors review answers, rapid-fire, scores & history; give feedback; unlock students; Admin rollup. |
| EPIC 11 — Dashboards | 1d | Day 19–20 | Role-specific dashboards for Admin, Mentor and Student. |
| EPIC 12 — Notifications | 0.5d | Day 20 | Email + in-app notifications for invites, launches, results and unlocks. |
| EPIC 13 — Internal QA, Polish & Demo Prep | 2d | Day 21–22 | Internally tested & polished build; demo data and UAT test plan ready. |
| EPIC 14 — UAT & Demo (1-week extension) | 3d | Day 23–25 | First client demo on UAT, defects fixed, regression passed — UAT SIGN-OFF. |
| EPIC 15 — Production Release & Go-Live (1-week extension) | 2d | Day 26–27 | Production deployed, go-live regression passed — PRODUCTION GO-LIVE SIGN-OFF. |
| TOTAL | 27d | Day 1–27 | 22-day build + 1-week UAT & production release. |

## 8.3 Detailed Breakdown

EPIC 0 — Designing & Planning   ·   2d   ·   Day 1–2

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Requirements & flow finalization | Finalize FRD, user flows, acceptance criteria | Plan | 0.5d |
| UI/UX design | Wireframes for all Admin + Student screens | FE | 0.75d |
| Architecture & data design | Database schema & ER design | DB | 0.25d |
|  | API contract / endpoint design | BE | 0.25d |
|  | Project plan, repo conventions, AI prompt strategy | Plan | 0.25d |

EPIC 1 — Foundation & Setup   ·   1d   ·   Day 3

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Project scaffolding | FastAPI project, config, Docker + Postgres | BE | 0.25d |
|  | Next.js app, Tailwind, base layout & routing | FE | 0.25d |
|  | Migrations baseline / ORM setup | DB | 0.2d |
| DevOps | Dev/CI environment + backend & DB hosting | DevOps | 0.15d |
|  | Frontend deploy (public URL) | DevOps | 0.15d |

EPIC 2 — Authentication & User Management   ·   2d   ·   Day 4–5

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Auth core | Email/password auth, JWT, temp-password → reset | BE | 0.4d |
|  | User & role tables | DB | 0.2d |
|  | Login + set-new-password screens (staff & student) | FE | 0.3d |
| Mentor invitation | Invite API + email with temp password | BE | 0.3d |
|  | Admin invite UI + mentor accept flow | FE | 0.2d |
| Student provisioning | CSV import + temp-password generation + email | BE | 0.3d |
|  | Student tables | DB | 0.1d |
|  | Admin student-import UI | FE | 0.2d |

EPIC 3 — Domain Management   ·   1d   ·   Day 6

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Domain CRUD | Domain table | DB | 0.1d |
|  | Domain CRUD API (Admin) | BE | 0.4d |
|  | Domain list + add/edit UI | FE | 0.5d |

EPIC 4 — Mentor Management & Domain Assignment   ·   1d   ·   Day 7

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Mentor management | Mentor list + domain-assignment API | BE | 0.4d |
|  | UserDomain mapping table | DB | 0.1d |
|  | Mentor management + assign-domains UI | FE | 0.4d |
|  | Domain-scoped authorization middleware | BE | 0.1d |

EPIC 5 — Case Study Authoring & Launch   ·   2d   ·   Day 8–9

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Authoring | CaseStudy + CaseStudyDomain + capability tables | DB | 0.2d |
|  | Case study CRUD (multi-domain, level, capabilities) | BE | 0.5d |
|  | Case study builder UI (scenario, level, domains) | FE | 0.6d |
| Launch | Publish + time-window + per-attempt-duration logic | BE | 0.35d |
|  | Launch UI + status lifecycle | FE | 0.35d |

EPIC 6 — AI Engine   ·   3.5d   ·   Day 10–13

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| LLM abstraction | LLMProvider interface + hosted-model integration | AI | 0.4d |
| Answer analysis | Analyze submission prompt + structured output | AI | 0.5d |
| Rapid-fire generation | Generate 3–4 probing questions from the answer | AI | 0.6d |
| Suggestions | ‘What is missing’ suggestion generation | AI | 0.5d |
| Scoring | Weighted rubric scoring (30/20/15/15/10/10) + JSON | AI | 0.7d |
| Reliability | Schema validation, retries, error/timeout handling | AI | 0.3d |
|  | Prompt tuning vs seeded cases + golden tests | AI | 0.5d |

EPIC 7 — Student Assessment Loop   ·   2.5d   ·   Day 13–15

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Briefing | Scenario briefing screen + Start + timer | FE | 0.25d |
| Answer (paste-blocked) | Answer editor with paste-block + visible timer | FE | 0.4d |
|  | Attempt create + answer persist + server timer | BE | 0.3d |
|  | Attempt / AttemptAnswer tables | DB | 0.15d |
| Rapid-fire round | Rapid-fire Q&A screen | FE | 0.35d |
|  | Wire to AI engine + persist responses | BE | 0.25d |
|  | RapidFire table | DB | 0.1d |
| Suggestions & 2nd submission | Suggestions + revise/resubmit screen | FE | 0.3d |
|  | Second-submission handling + final-score trigger | BE | 0.2d |
| Final score | Score breakdown screen (6 dimensions) | FE | 0.2d |

EPIC 8 — Level Progression Engine   ·   1d   ·   Day 16

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Progression logic | Progression rules (pass/retry/lock, configurable <33%) | BE | 0.4d |
|  | StudentDomain level/status + attempt cap | DB | 0.15d |
|  | Auto-advance + lock + unlock APIs | BE | 0.25d |
|  | Progression feedback UI (pass/retry/locked banner) | FE | 0.2d |

EPIC 9 — Capability Scoring & Profile   ·   1d   ·   Day 17

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Capability scoring | Capability + StudentCapability tables | DB | 0.15d |
|  | Score update from attempts + capability mapping | BE | 0.35d |
|  | Student capability profile + trend graph | FE | 0.5d |

EPIC 10 — Reporting & Feedback   ·   1.5d   ·   Day 18–19

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Reporting | Roster + individual report APIs | BE | 0.4d |
|  | Mentor report screens | FE | 0.45d |
| Feedback & unlock | Feedback + unlock APIs | BE | 0.2d |
|  | Feedback + unlock UI | FE | 0.2d |
| Admin rollup | Cross-domain rollup API | BE | 0.15d |
|  | Rollup view | FE | 0.1d |

EPIC 11 — Dashboards   ·   1d   ·   Day 19–20

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Admin dashboard | Stats API | BE | 0.15d |
|  | Admin dashboard UI | FE | 0.25d |
| Mentor dashboard | Mentor dashboard (attention items) | FE | 0.25d |
| Student dashboard | Student dashboard (scores, tasks, progress) | FE | 0.35d |

EPIC 12 — Notifications   ·   0.5d   ·   Day 20

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Notifications | Email triggers + in-app notification API | BE | 0.3d |
|  | Notification table | DB | 0.05d |
|  | In-app notification list | FE | 0.15d |

EPIC 13 — Internal QA, Polish & Demo Prep   ·   2d   ·   Day 21–22

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Internal QA | End-to-end testing across all flows + bug fixing | QA | 0.8d |
| Polish | UI polish, empty / loading / error states | FE | 0.5d |
| Prep | Seed demo data + UAT test plan | Plan | 0.4d |
|  | Build hardening | BE | 0.3d |

EPIC 14 — UAT & Demo (1-week extension)   ·   3d   ·   Day 23–25

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| UAT deployment | Provision & deploy to UAT environment | DevOps | 0.5d |
| Demo & acceptance | First client demo on UAT | PM | 0.5d |
|  | UAT sign-off coordination | PM | 0.3d |
| UAT testing & fixes | UAT regression testing | QA | 1d |
|  | UAT defect fixes | Dev | 0.7d |

EPIC 15 — Production Release & Go-Live (1-week extension)   ·   2d   ·   Day 26–27

| Task | Subtask | Layer | Effort |
| --- | --- | --- | --- |
| Production deployment | Provision production environment + deploy | DevOps | 0.7d |
|  | Go-live cutover + monitoring/alerts setup | DevOps | 0.4d |
| Go-live verification | Go-live regression / smoke testing | QA | 0.6d |
|  | Production go-live sign-off | PM | 0.3d |

# 9. Assumptions & Notes

- Delivery is 27 working days: a 22-day build (Day 1–22) plus a 1-week extension (Day 23–27) for UAT and production release.

- The first client demo is on the UAT environment; UAT sign-off precedes production deployment, which ends in a go-live sign-off.

- Effort-day estimates are timeline-aligned and assume the resourcing in §4 (developer full-time; PM 40%; QA weekly sanity + UAT/Live regression; DevOps 30%). Some FE/BE/DB work interleaves within a module.

- Scope is a PoC: email/password auth with temp-password onboarding (no SSO); hosted LLM behind an abstraction (Llama 3.3 targeted for production); vector DB, mobile app, WhatsApp/SMS and digital twin are out of scope.

- Single college; single domain per student; banded case-study visibility — per the FRD. Open decisions (e.g. behaviour below 33%) are built configurable and do not affect the timeline.

# 10. Open Queries (Pending Client Inputs)

Living list of items awaiting client confirmation. Resolving these does not block the build (defaults are in place), but they are needed before UAT sign-off and go-live.

| # | Open Query | Area / Reference | Status |
| --- | --- | --- | --- |
| 1 | Behaviour when a student scores below 33% — hard-lock the level immediately, or simply consume one of the 4 attempts? | FRD BR-3 | Open |
| 2 | Single-college only, or is multi-college data isolation required? | FRD §11 | Open |
| 3 | How should an attempt's score map to the capability taxonomy (which capabilities, weighting)? | FRD FR-S6.4 | Open |
| 4 | Confirm hosted LLM for the PoC with Llama 3.3 as the production target — acceptable? | Technology | Open |
| 5 | Who provides the production environment / hosting, domain name and SSL certificate? | DevOps / Go-Live | Open |
| 6 | Required format and a sample of the student CSV (fields, college identifiers). | Student provisioning | Open |
| 7 | Transactional email service and sender domain for invitations, credentials and notifications. | Notifications | Open |
| 8 | Branding / UI guidelines (logo, colours, fonts) for the portals. | UI/UX | Open |
| 9 | Number of domains and seeded case studies required for the UAT demo. | Demo content | Open |
| 10 | Client availability / dates for the UAT demo, UAT sign-off and the go-live window. | Schedule | Open |
| 11 | Confirm banded case-study visibility (current level only) vs cumulative. | FRD FR-S3 | Open |
| 12 | Confirm scoring standing = best score across attempts (vs latest). | FRD BR-2 | Open |